Proposal submitted by: [OFFEROR ORGANIZATION NAME]

IFP 2026-AS-9400

Access to Services through Knowledge (ASK) Web-based Platform

Work Plan Template

| Proposer's Unique Plans for Implementing the Scope of Work | Start Work | Complete Work | Ongoing Work | Staff and/or Providers (Performing & Oversight) |
| --- | --- | --- | --- | --- |
| Convene Advisory Committee (Meeting #1): present project kickoff, timeline, and communication plan; gather initial input on platform priorities and content organization. | 10/1/26 | 10/31/26 |  | Project Director (oversight) Advisory Committee Liaison (execution) |
| Conduct technology review and analysis of existing vs. new platform options (functionality, scalability, security, cost, intuitiveness); document findings in Technology Review and Analysis Outcome Report. Begin technical architecture planning for new custom-built platform, including accessibility (Section 508 / WCAG 2.1-2.2 AA) requirements and AI search/chat feasibility assessment. | 11/1/26 | 11/30/26 |  | Technical Lead / Solutions Architect (execution) Accessibility Specialist (oversight) |
| Present Technology Review and Analysis Outcome Report to Advisory Committee (Meeting #2) to confirm modality decision (new platform build). *Modality confirmation completed within 90 days of contract execution. Finalize platform architecture, information architecture (IA), and site map incorporating the 5 content module types (case studies, decision aids, explainers, roadmaps, mindmaps). | 12/1/26 | 12/31/26 |  | Project Director (oversight) Technical Lead (execution) UX/IA Designer (execution) |
| Design wireframes and prototype for platform landing page, topic/domain navigation, life-stage navigation, and family story navigation, modeled on the Phase 2 personas and journey maps. | 1/1/27 | 1/31/27 |  | UX/UI Designer (execution) Technical Lead (oversight) |
| Begin front-end and back-end development of the ASK platform; integrate searchable/navigable structure for content modules. Begin design and integration of AI-supported search, chat, and content navigation features, with protocols suited to a potentially vulnerable end-user population. | 2/1/27 | 2/28/27 |  | Development Team (execution) AI/NLP Engineer (execution) Technical Lead (oversight) |
| Continue platform development; populate initial content modules (Early Intervention, Education, Decision-Making Supports) into the platform structure. Convene Advisory Committee (Meeting #3): demo in-progress platform and content population; gather feedback. | 3/1/27 | 3/31/27 |  | Development Team (execution) Content Integration Specialist (execution) Advisory Committee Liaison (execution) |
| Continue content population (Asset Management/Financial Planning, Employment and Volunteering, Social Connection, Supports and Services, Behavioral Health, Diagnosis modules) across all 62 content files spanning 40+ modules. Conduct internal QA testing and accessibility testing (Section 508 / WCAG 2.1-2.2 AA) on completed platform sections. | 4/1/27 | 4/30/27 |  | Content Integration Specialist (execution) QA/Accessibility Tester (execution) Technical Lead (oversight) |
| Complete full content population across all modules and domains. Finalize AI search/chat feature testing and refinement. Conduct comprehensive accessibility audit and remediate identified issues. | 5/1/27 | 5/31/27 |  | Development Team (execution) QA/Accessibility Tester (execution) AI/NLP Engineer (execution) |
| Convene Advisory Committee (Meeting #4): present near-final platform for review and buy-in. Implement user testing with a minimum of one small group of family members of individuals with I/DD; collect and document feedback. | 6/1/27 | 6/30/27 |  | Project Director (oversight) UX Researcher (execution) Advisory Committee Liaison (execution) |
| Incorporate user testing feedback into platform refinements. Conduct final round of accessibility and QA testing to confirm compliance and platform stability. | 7/1/27 | 7/31/27 |  | Development Team (execution) QA/Accessibility Tester (execution) |
| Finalize platform for launch readiness; prepare End User manual content from platform mapping and integrated capabilities documentation. *Platform and user testing completed prior to September 30, 2027. | 8/1/27 | 8/31/27 |  | Technical Lead (execution) Documentation Specialist (execution) Project Director (oversight) |
| Launch ASK web-based platform. Prepare and submit Final Comprehensive Report (mapping and integrated capabilities) and Executive Summary (overview of activities, outputs, outcomes, data summary, recommendations for future action). | 9/1/27 | 9/30/27 | Testing, measurement, and continuous improvement plan begins post-launch and continues through the contract period and beyond. | Project Director (oversight) Technical Lead (execution) Documentation Specialist (execution) |

Note: In addition to the monthly milestones above, the following deliverables recur every month of the contract period, per Council programmatic requirements: (1) an updated work plan; (2) a monthly project progress report including wireframe/prototype status and deliverable status indicators (in progress, completed, idle); and (3) participation in regularly scheduled meetings with FDDC program staff.

Instructions for completing the Work Plan Template:

• Proposers must describe their unique plans for implementing the scope of work, including how it will be implemented, in the left-hand column.

• Proposers must populate all facets of work using the monthly time frame for beginning, completing, or ongoing work for each task.

• Proposers must populate the right-hand column to designate the staff and/or providers who will be responsible for performing and providing oversight for each task reflected in the left-hand column.

• Proposers may add rows as needed.